HUMAN vs. AI

Analysing the Advancement of AI in Music Mastering

Student:  Michael Adams

Programme:  MSc Music and Media Technologies

Institution:  Trinity College Dublin

Duration:  8 Weeks (2 Months)

Document:  Project Plan

PROJECT OVERVIEW

This project investigates the current state of AI-driven music mastering by conducting a rigorous blind comparison between professionally mastered tracks and AI-mastered equivalents. Through structured listening tests with diverse participant groups, the study aims to determine whether modern AI mastering tools have reached a level of quality that is perceptually comparable to human mastering engineers.

Summary Timeline

| Week | Phase | Key Activities |
| --- | --- | --- |
| 1 | Preparation | Literature review, song selection, ethics |
| 2 | Preparation | Engage engineers, begin AI research |
| 3 | Production | Process AI masters, design blind test |
| 4 | Production | Normalise audio, build test platform, pilot |
| 5 | Testing | Recruit participants, begin blind tests |
| 6 | Testing | Complete tests, preliminary analysis |
| 7 | Analysis | Deep analysis, begin thesis writing |
| 8 | Analysis | Conclusions, final write-up, presentation |

WEEK 1   |   PREPARATION

Research, Planning & Song Selection

Objectives

Finalise the research methodology and evaluation framework

Select and curate a diverse set of pre-mastered songs for the study

Tasks

1. Literature Review & Background Research

Survey existing academic literature on AI mastering (LANDR, CloudBounce, iZotope Ozone AI, Dolby.io, BandLab, eMastered, etc.)

Review prior comparative studies on human vs. AI audio processing

Document the current landscape of AI mastering technology

2. Song Selection & Curation

Select 4–6 pre-mastered songs spanning different genres (e.g., rock, electronic, jazz, classical, pop, singer-songwriter)

Ensure songs vary in dynamic range, instrumentation density, and tonal complexity

Source songs where you have permission to use them (original compositions, Creative Commons, or artist-permitted tracks)

Ensure all tracks are high-quality unmastered mixes (minimum 24-bit WAV)

3. Ethics & Permissions

Confirm ethical approval requirements with TCD for human listening tests

Prepare participant consent forms and information sheets

Secure written permission for use of any third-party music

Deliverables

✓  Finalised song list with rationale for each selection

✓  Literature review summary document

✓  Ethics/consent documentation drafted

WEEK 2   |   PREPARATION

Engage Professional Mastering Engineers

Objectives

Identify and engage 2–3 professional mastering engineers

Provide them with the selected tracks and clear briefs

Tasks

1. Engineer Identification & Outreach

Research and shortlist mastering engineers (ideally with varying experience levels and studio setups)

Contact engineers with a clear project brief explaining the academic purpose

Agree on timelines, fees (if applicable), and deliverable formats

2. Brief Preparation & Delivery

Prepare a standardised mastering brief for each song (target loudness, format requirements, genre-specific notes)

Provide all engineers with identical source files (same format, sample rate, bit depth)

Request masters in 16-bit/44.1kHz WAV (CD quality) as well as 24-bit/48kHz for analysis

Ask engineers NOT to add any unique identifiers (fades, tags, etc.)

3. Begin AI Mastering Research

Identify 2–3 AI mastering platforms to test (e.g., LANDR, CloudBounce, iZotope Ozone AI Assistant)

Create accounts and familiarise yourself with each platform’s workflow

Document the feature sets, pricing tiers, and configuration options of each tool

Deliverables

✓  Confirmed list of participating mastering engineers

✓  Mastering briefs sent to all engineers

✓  AI mastering platform shortlist with feature comparison

WEEK 3   |   PRODUCTION

AI Mastering & Preliminary Collection

Objectives

Master all songs through the selected AI platforms

Begin collecting completed human masters

Design the blind test framework

Tasks

1. AI Mastering Execution

Process each song through each selected AI mastering platform

Experiment with available settings (genre presets, loudness targets, tonal adjustments)

Select the best AI master from each platform for each song (or use default settings for consistency — document your decision)

Export all AI masters in matching formats (16-bit/44.1kHz and 24-bit/48kHz WAV)

2. Documentation of AI Process

Screenshot and document all settings used for each AI master

Record processing times and any limitations encountered

Note any songs where AI tools struggled or produced unexpected results

3. Blind Test Design

Design the listening test methodology (ABX, MUSHRA, or custom scoring approach)

Define scoring criteria (e.g., clarity, punch, warmth, stereo image, dynamics, overall preference)

Use a Likert scale (1–10) for each criterion

Plan the listening environment requirements (headphones vs. speakers, room acoustics)

Deliverables

✓  Complete set of AI-mastered tracks (all songs × all platforms)

✓  AI mastering process documentation

✓  Blind test methodology document

WEEK 4   |   PRODUCTION

Collection, Normalisation & Test Preparation

Objectives

Collect all human masters

Normalise and prepare all tracks for blind testing

Build the listening test infrastructure

Tasks

1. Collect Human Masters

Follow up with engineers and collect all completed masters

Verify file formats and quality match specifications

Address any issues or request revisions if needed

2. Audio Normalisation & Preparation

Loudness-normalise all masters (human and AI) to a consistent level (e.g., −14 LUFS integrated)

This is critical — loudness differences bias listeners toward louder versions

Trim all tracks to identical start/end points

Randomise and assign anonymous labels (e.g., “Version A”, “Version B”, “Version C”)

Create a master reference document mapping labels to sources (keep strictly confidential)

3. Test Platform Setup & Pilot

Set up the listening test platform (webMUSHRA, Google Forms, or custom web app)

Upload all anonymised audio files

Create the questionnaire with scoring criteria and demographic questions

Run a pilot test with 2–3 people to validate the flow

Refine based on pilot feedback

Deliverables

✓  All mastered tracks collected, normalised, and anonymised

✓  Functional listening test platform

✓  Pilot test completed with feedback incorporated

WEEK 5   |   TESTING

Recruit Participants & Begin Blind Testing

Objectives

Recruit a diverse pool of listeners

Begin conducting blind listening tests

Tasks

1. Participant Recruitment

Recruit from MMT classmates (trained ears, music technology background)

Recruit from other TCD music students (performance, composition, musicology)

Engage professional musicians/engineers (external contacts)

Include general listeners (non-musicians for broader perspective)

Aim for a minimum of 20–30 participants across groups

Distribute consent forms and collect signed agreements

2. Listening Test Sessions

Schedule and conduct listening test sessions

Provide consistent listening conditions where possible

For remote participants, provide clear instructions on playback requirements

Monitor for test fatigue — keep individual sessions under 30–40 minutes

3. Data Collection

Record all responses in a structured format (spreadsheet/database)

Track participant metadata (group, experience level, listening setup)

Note any technical issues or anomalies during sessions

Deliverables

✓  Minimum 15+ completed listening tests by end of week

✓  Organised raw data spreadsheet

✓  Participant log with demographics

WEEK 6   |   TESTING

Complete Testing & Begin Analysis

Objectives

Complete all remaining listening tests

Begin preliminary data analysis

Tasks

1. Complete Remaining Tests

Follow up with outstanding participants

Conduct any remaining in-person sessions

Close the test window and finalise data collection

2. Data Cleaning & Organisation

Clean and validate all collected data

Remove incomplete responses or flag outliers

Organise data by participant group, song, and mastering source

3. Preliminary Statistical Analysis

Calculate mean scores and standard deviations for each version of each song

Compare human vs. AI scores across all evaluation criteria

Break down results by participant group (expert vs. general listener)

Generate initial charts and visualisations

Consider statistical tests: paired t-tests, ANOVA, or Wilcoxon signed-rank tests

Deliverables

✓  Complete dataset (all participants)

✓  Preliminary analysis with initial charts

✓  Identified trends and patterns

WEEK 7   |   ANALYSIS

Deep Analysis & Thesis Writing

Objectives

Conduct comprehensive statistical analysis

Begin writing the thesis/report

Tasks

1. Comprehensive Analysis

Overall preference: Human vs. AI

Per-criterion analysis (clarity, dynamics, warmth, etc.)

Genre-dependent performance (does AI do better with certain genres?)

Expert vs. non-expert perception differences

Platform-specific performance (which AI tool performed best?)

Calculate statistical significance for key findings

Create publication-quality charts, graphs, and tables

2. Spectral & Technical Analysis (Optional Enhancement)

Perform spectral analysis comparing human and AI masters (frequency response, dynamic range, stereo width)

Use tools like iZotope Insight, SPAN, or Python (librosa) for technical measurements

Correlate technical differences with perceptual scores

3. Begin Thesis Writing

Introduction and literature review

Methodology chapter (detailed description of the entire process)

Results chapter (present findings with supporting data)

Deliverables

✓  Complete statistical analysis with all charts and tables

✓  Draft of Introduction, Literature Review, and Methodology chapters

✓  Technical analysis report (if included)

WEEK 8   |   COMPLETION

Conclusions, Final Write-Up & Presentation

Objectives

Draw conclusions from the analysis

Complete the thesis document

Prepare the final presentation

Tasks

1. Conclusions & Discussion

Has AI mastering reached professional quality?

Where does AI excel and where does it fall short?

What are the implications for the music industry?

What are the limitations of this study?

Discuss future directions and recommendations

2. Complete Thesis Document

Write the Discussion and Conclusions chapters

Write the Abstract

Compile references and bibliography

Proofread and format the entire document

Ensure all appendices are included (consent forms, raw data, test materials)

3. Final Presentation & Submission

Create a presentation summarising the project and key findings

Rehearse the presentation

Prepare for Q&A from supervisors and lecturers

Final proofread, quality check, and submit

Deliverables

✓  Completed thesis document

✓  Final presentation

✓  All supporting materials and raw data archived

RISK MITIGATION

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Engineer Delays | Delays Week 4 tasks | Engage engineers early; have backup engineers identified |
| Low Participant Count | Weakens statistical significance | Start recruitment in Week 3; leverage social media and course networks |
| AI Platform Limitations | Incomplete AI dataset | Test platforms early in Week 2; have backup platforms ready |
| Test Platform Issues | Delays testing | Pilot test in Week 4; have offline backup (USB + paper forms) |
| Ethics Approval Delays | Blocks testing phase | Submit ethics application in Week 1; follow up proactively |

TOOLS & RESOURCES

AI Mastering Platforms

LANDR (landr.com)

CloudBounce (cloudbounce.com)

eMastered (emastered.com)

iZotope Ozone AI Assistant

BandLab Mastering (bandlab.com)

Dolby.io Media Mastering

Analysis Tools

Python (librosa, scipy, matplotlib) for audio and statistical analysis

SPSS or R for advanced statistics

iZotope Insight / Voxengo SPAN for spectral analysis

Excel / Google Sheets for data organisation

Listening Test Platforms

webMUSHRA (open-source, designed for audio quality evaluation)

Google Forms + cloud-hosted audio

Custom web application (if needed)