## Slide 1
HUMAN vs. AI
Analysing the Advancement of AI in Music Mastering
MSc Music and Media Technologies | Trinity College Dublin
Michael Adams
Project Plan Presentation | 2025

## Slide 2
RESEARCH QUESTION
Has AI mastering technology advanced to a point where it is perceptually indistinguishable from professional human mastering?
This study conducts a rigorous blind comparison between professionally mastered tracks and AI-mastered equivalents, evaluated by diverse listener groups.
Comparative
Blind A/B testing of human vs. AI mastered tracks
Perceptual
Listener scoring across multiple audio quality criteria
Statistical
Data-driven analysis with diverse participant groups

## Slide 3
METHODOLOGY
Five-Stage Research Process
01
Collect
Curate diverse pre-mastered songs
▶
02
Human Master
Engage professional mastering engineers
▶
03
AI Master
Process through leading AI platforms
▶
04
Blind Test
Structured listening tests with scoring
▶
05
Analyse
Statistical analysis & conclusions

## Slide 4
PROJECT TIMELINE
8-Week Plan Overview
PREPARATION
PRODUCTION
TESTING
ANALYSIS
WK 1
Research & Song Selection
WK 2
Engage Engineers
WK 3
AI Mastering & Test Design
WK 4
Normalise & Test Prep
WK 5
Begin Blind Testing
WK 6
Complete Tests & Early Analysis
WK 7
Deep Analysis & Writing
WK 8
Conclusions & Submission
KEY MILESTONES
✓ Week 2: Engineers engaged & AI platforms selected
✓ Week 4: All masters collected, normalised & test platform ready
✓ Week 6: All listening tests completed
✓ Week 8: Thesis submitted

## Slide 5
WEEKS 1-2 | PREPARATION
Research, Song Selection & Engineer Engagement
Week 1: Research & Song Selection
Survey academic literature on AI mastering
Review prior human vs. AI audio studies
Select 4-6 pre-mastered songs across genres
Ensure genre diversity (rock, electronic, jazz, pop, etc.)
Source high-quality unmastered mixes (24-bit WAV)
Secure permissions for all tracks
Submit ethics application for listening tests
Prepare participant consent forms
Week 2: Engage Mastering Engineers
Shortlist 2-3 professional mastering engineers
Contact engineers with academic project brief
Agree timelines, fees & deliverable formats
Prepare standardised mastering briefs
Provide identical source files to all engineers
Request 16-bit/44.1kHz + 24-bit/48kHz masters
Identify 2-3 AI mastering platforms to test
Document AI platform features & capabilities

## Slide 6
WEEKS 3-4 | PRODUCTION
AI Mastering, Normalisation & Test Preparation
Week 3: AI Mastering & Test Design
Process all songs through each AI platform
Experiment with settings (presets, loudness, tone)
Document all AI settings with screenshots
Record processing times & limitations
Export AI masters in matching formats
Design listening test methodology (ABX/MUSHRA)
Define scoring criteria (clarity, punch, warmth, etc.)
Plan Likert scale (1-10) evaluation framework
Week 4: Normalise & Build Test Platform
Collect all completed human masters
Loudness-normalise all tracks (e.g., -14 LUFS)
Trim tracks to identical start/end points
Assign anonymous labels (Version A, B, C...)
Set up listening test platform (webMUSHRA / Forms)
Upload all anonymised audio files
Create questionnaire with demographic questions
Run pilot test with 2-3 people & refine

## Slide 7
WEEKS 5-6 | TESTING
Blind Listening Tests & Early Analysis
Week 5: Recruit & Begin Testing
Recruit from MMT classmates (trained ears)
Recruit from TCD music students
Engage professional musicians/engineers
Include general listeners (non-musicians)
Target 20-30 participants minimum
Distribute & collect consent forms
Conduct listening test sessions
Keep sessions under 30-40 minutes
Week 6: Complete Tests & Early Analysis
Follow up with outstanding participants
Close test window & finalise data collection
Clean & validate all collected data
Remove incomplete / flag outlier responses
Calculate mean scores & standard deviations
Compare human vs. AI across all criteria
Break down by participant group
Generate initial charts & visualisations

## Slide 8
WEEKS 7-8 | ANALYSIS & COMPLETION
Deep Analysis, Conclusions & Submission
Week 7: Deep Analysis & Writing
Overall preference analysis: Human vs. AI
Per-criterion breakdown (clarity, dynamics, etc.)
Genre-dependent performance analysis
Expert vs. non-expert perception differences
Platform-specific AI performance comparison
Statistical significance testing (t-test, ANOVA)
Optional: Spectral analysis (frequency, stereo width)
Begin writing: Intro, Literature Review, Methodology
Week 8: Conclusions & Submission
Synthesise findings into clear conclusions
Has AI mastering reached professional quality?
Where does AI excel? Where does it fall short?
Implications for the music industry
Discuss limitations & future directions
Complete Discussion & Conclusions chapters
Write Abstract, compile references
Final proofread, format & submit

## Slide 9
TOOLS & TECHNOLOGY
Platforms, Software & Analysis Tools
AI Mastering Platforms
LANDR
CloudBounce
eMastered
iZotope Ozone AI
BandLab Mastering
Dolby.io Media Mastering
Analysis Tools
Python (librosa, scipy)
matplotlib / seaborn
SPSS or R for statistics
iZotope Insight
Voxengo SPAN
Excel / Google Sheets
Listening Test Platforms
webMUSHRA (open-source)
Google Forms + audio
Custom web application
Quality headphones / monitors
Treated listening room
Reference DAW (Logic/Reaper)

## Slide 10
RISK MITIGATION
Identified Risks & Contingency Plans
Engineer Delays
Mastering engineers may not deliver on time
Mitigation:
Engage engineers early in Week 2; identify backup engineers
Low Participant Count
Insufficient listeners weakens statistical significance
Mitigation:
Start recruitment in Week 3; use social media & course networks
AI Platform Limitations
Tools may not support certain genres or formats
Mitigation:
Test platforms early in Week 2; have backup platforms ready
Test Platform Issues
Technical problems during listening sessions
Mitigation:
Pilot test in Week 4; prepare offline backup (USB + paper)
Ethics Approval Delays
Late approval blocks participant testing
Mitigation:
Submit ethics application in Week 1; follow up proactively

## Slide 11
Thank You
Questions & Discussion
Michael Adams | MSc Music & Media Technologies | Trinity College Dublin